## OASIS
(Transmission lines rated 138kV and higher that limit bulk power transfers are listed)
Nova Scotia Power |  |  |  | For help, contact: |  |  |  |  | FIM (Flow into Metro) |  | Last Update: | Legend
Transmission Operations |  |  |  | nspsoadmin@nspower.ca | [6 empty] | 2025-04-25 10:30 | Please note all Planned Outages in Green indicates new updates
Transmission Planned Outage Schedule
Circuit/Element | For Work On | Start Date | Return Date | Reason | CBX | ONI | ONS | EEX@EB | MDRR | FIM | Generation Restrictions | Import/Export | Notes | Work Status
NB STOP 002 | NB STOP 002 | 2025-04-04 | 2025-06-20 | [7 empty] | #VALUE!
101S-T81 | 101S-T81 | 2025-04-14 | 2025-04-25 | [7 empty] | Carry reserve for full ML flows 1 VJ required on Sync
99W-B61 | 99W-B61 | 4/22/2025 0600 | 4/25/2025 1600 | [7 empty] | Brooklyn Power required to run at 20 MW minimum Tusket CT required available
99W-B62 | 99W-B62 | 2025-04-28 | 2025-05-02 | [7 empty] | Brooklyn Power required to run at 20 MW minimum Tusket CT required available