## OASIS
(Transmission lines rated 138kV and higher that limit bulk power transfers are listed)
Nova Scotia Power |  |  |  | For help, contact: |  |  |  |  | FIM (Flow into Metro) |  | Last Update: | Legend
Transmission Operations |  |  |  | nspsoadmin@nspower.ca | [6 empty] | 2025-06-09 15:50 | Please note all Planned Outages in Green indicates new updates
Transmission Planned Outage Schedule
Circuit/Element | For Work On | Start Date | Return Date | Reason | CBX | ONI | ONS | EEX@EB | MDRR | FIM | Generation Restrictions | Import/Export | Notes | Work Status
NB STOP 002 | NB STOP 002 | 2025-04-04 | 2025-06-20 | [8 empty] | #VALUE!
L-6021 | L-6021 | 2025-05-27 | 2025-06-26 | [7 empty] | TK4 is required available
88S-T72 | 88S-T72 | 2025-06-09 | 2025-06-27 | [7 empty] | - 88S-T71 is restricted to 170 MW. - Wreck Cove (Total) limited to 150 MW. - VJ1 and VJ2 must be run on Sync |  | - Cape Breton Export is restricted to 1120 MW.
L-7005 | L-7005 | 2025-06-03 | 2025-07-04 | Transmission Line Maintenance | [6 empty] | Trenton 6 must run |  | Mainland at Hastings limited to 385MWs CBX limited to 760 MWs ONI limited to 930 MWs
NB STOP 010 | NB STOP 010 | 2025-06-06 | 2025-06-13 | [8 empty] | #VALUE!
LIL POLE 1 OUTAGE | LIL POLE 1 OUTAGE | 2025-09-14 | 2025-09-20
LIL BIPOLE OUTAGE | LIL BIPOLE OUTAGE | 2025-09-21 | 2025-09-30
LIL POLE 1 OUTAGE | LIL POLE 1 OUTAGE | 2025-10-01 | 2025-10-14